## Project Overview
CONSULTANCY ENGAGEMENT — IMPLEMENTATION PLAN
Change Management & Training Services
Client: |  |  | Milestone Global Bank (MGB)
Consultant: |  |  | Mr. Ibrahim Khalil
Effective Date: |  |  | 13 February 2026
Duration: |  |  | 6 Months (February – August 2026)
ENGAGEMENT SCOPE SUMMARY
Task # | Work Stream | Key Focus Areas |  | Key Deliverables | Timeline
1 | Change Management Plan | Communications strategy, change champion recruitment & coordination, resistance management, feedback loops |  | Approved Communication Plan, Change Charter, Champion Network Roster, Feedback Loop Reports | Months 1–2
2 | Role-Based Training & Onboarding | Training needs assessment, role-based content design, training delivery across all cohorts, knowledge checks, attendance tracking |  | Training Reports, Attendance Records, Post-Training Assessment Scores, Onboarding Guide | Months 2–4
3 | Change Champion Network | Champion identification, activation sessions, monthly coordination, feedback aggregation, recognition programme |  | Champion Network Roster, Monthly Champion Reports, Adoption Feedback Logs | Months 2–6
4 | Adoption Surveys & Scorecards | Baseline pulse survey, mid-point assessment, scorecard design and validation, trend analysis |  | Adoption Surveys (Baseline, Mid, Final), Adoption Scorecards, Trend Analysis Reports | Months 3–5
5 | Post–Go-Live Adoption Tracking | Go-live readiness review, post-launch user monitoring, weekly adoption tracking, corrective actions, final metrics |  | Go-Live Readiness Report, Weekly Adoption Tracker, Final Adoption Metrics Report (≥80%) | Months 5–6
KEY PERFORMANCE INDICATORS (KPIs)
KPI 1 | Timely delivery of all phased deliverables per retainership schedule
KPI 2 | Change adoption score ≥80% achieved across all user groups at Month 6
KPI 3 | Training completion rate ≥90% across all role-based cohorts
KPI 4 | Documentation suitable for CBN audit and regulatory review by Month 6
KPI 5 | Responsiveness to Digibit/MGB queries within 48 hours
15D, Yalinga Street, Off Adetokunbo Ademola Crescent, Wuse II, FCT, Nigeria ¦ +234 815 177 8448 ¦ connect@globaldigibit.com ¦ globaldigibit.com

## Implementation Timeline
DETAILED IMPLEMENTATION TIMELINE
# | Activity / Milestone | Responsible | Status | Month 1 (Feb-Mar) |  |  |  | Month 2 (Mar-Apr) |  |  |  | Month 3 (Apr-May) |  |  |  | Month 4 (May-Jun) |  |  |  | Month 5 (Jun-Jul) |  |  |  | Month 6 (Jul-Aug)
|  |  |  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24
TASK 1: CHANGE MANAGEMENT PLAN
1.1 | Kick-off session — Digibit & MGB leadership alignment | Khalil / Digibit | Not Started | bar: Month 1 (Feb-Mar) W1 to Month 1 (Feb-Mar) W4
1.2 | Change governance structure established (charter, workstreams) | Khalil | Not Started | bar: Month 1 (Feb-Mar) W3 to Month 2 (Mar-Apr) W8
1.3 | Stakeholder identification & impact mapping | Khalil | Not Started | bar: Month 1 (Feb-Mar) W4 to Month 2 (Mar-Apr) W7
1.4 | Change communication strategy developed & approved | Khalil / Digibit | Not Started | bar: Month 2 (Mar-Apr) W5 to Month 3 (Apr-May) W12
1.5 | Communication campaign Wave 1 executed | Khalil / Digibit | Not Started | bar: Month 2 (Mar-Apr) W8 to Month 4 (May-Jun) W14
1.6 | Change champion identification & recruitment | Khalil / MGB HR | Not Started | bar: Month 3 (Apr-May) W12 to Month 5 (Jun-Jul) W17
1.7 | Champion activation session (roles, tools, escalation) | Khalil | Not Started | bar: Month 4 (May-Jun) W14 to Month 5 (Jun-Jul) W18
1.8 | Resistance risk log maintained & mitigation tracked | Khalil | Not Started | bar: Month 5 (Jun-Jul) W18 to Month 6 (Jul-Aug) W21
1.9 | Communication campaign Wave 2 — post go-live reinforcement | Khalil / Digibit | Not Started | bar: Month 6 (Jul-Aug) W21 to Month 6 (Jul-Aug) W24
★ | MILESTONE: Change Charter & Communication Plan Approved |  | Pending | bar: Month 4 (May-Jun) W14
★ | MILESTONE: Change Champion Network Fully Activated |  | Pending | bar: Month 6 (Jul-Aug) W24
TASK 2: ROLE-BASED TRAINING & ONBOARDING
2.1 | Training needs assessment (role-based segmentation) | Khalil | Not Started | bar: Month 1 (Feb-Mar) W1 to Month 2 (Mar-Apr) W6
2.2 | Role-based training content design & materials development | Khalil | Not Started | bar: Month 1 (Feb-Mar) W3 to Month 2 (Mar-Apr) W8
2.3 | Onboarding framework developed for new system users | Khalil | Not Started | bar: Month 2 (Mar-Apr) W5 to Month 3 (Apr-May) W10
2.4 | Training delivery — Cohort 1 (operations & frontline) | Khalil | Not Started | bar: Month 2 (Mar-Apr) W8 to Month 4 (May-Jun) W14
2.5 | Training delivery — Cohort 2 (management & supervisors) | Khalil | Not Started | bar: Month 3 (Apr-May) W12 to Month 4 (May-Jun) W16
2.6 | Training delivery — Cohort 3 (executives & senior mgmt) | Khalil | Not Started | bar: Month 3 (Apr-May) W10 to Month 4 (May-Jun) W16
2.7 | Remedial training sessions for underperforming cohorts | Khalil | Not Started | bar: Month 4 (May-Jun) W16 to Month 6 (Jul-Aug) W22
2.8 | Knowledge transfer & operational training handover | Khalil | Not Started | bar: Month 5 (Jun-Jul) W18 to Month 6 (Jul-Aug) W22
2.9 | Final training documentation archive compiled | Khalil | Not Started | bar: Month 6 (Jul-Aug) W22 to Month 6 (Jul-Aug) W24
★ | MILESTONE: Training Modules Finalised & All Cohorts Completed |  | Pending | bar: Month 2 (Mar-Apr) W6
★ | MILESTONE: Training Documentation Archive Delivered |  | Pending | bar: Month 6 (Jul-Aug) W24
TASK 3: CHANGE CHAMPION NETWORK
3.1 | Champion network roster & directory finalised | Khalil | Not Started | bar: Month 1 (Feb-Mar) W1 to Month 2 (Mar-Apr) W6
3.2 | Monthly champion coordination session (Month 2) | Khalil | Not Started | bar: Month 1 (Feb-Mar) W4 to Month 2 (Mar-Apr) W8
3.3 | Monthly champion coordination session (Month 3) | Khalil | Not Started | bar: Month 2 (Mar-Apr) W6 to Month 3 (Apr-May) W12
3.4 | Monthly champion coordination session (Month 4) | Khalil | Not Started | bar: Month 2 (Mar-Apr) W8 to Month 4 (May-Jun) W14
3.5 | Monthly champion coordination session (Month 5) — go-live | Khalil | Not Started | bar: Month 4 (May-Jun) W14 to Month 5 (Jun-Jul) W20
3.6 | Feedback aggregation — champion reports per session | Khalil | Not Started | bar: Month 5 (Jun-Jul) W18 to Month 6 (Jul-Aug) W21
3.7 | Recognition & engagement programme for active champions | Khalil | Not Started | bar: Month 5 (Jun-Jul) W20 to Month 6 (Jul-Aug) W24
3.8 | Champion network handover to MGB internal leads | Khalil | Not Started | bar: Month 6 (Jul-Aug) W22 to Month 6 (Jul-Aug) W24
★ | MILESTONE: Champion Network Activation Report Issued |  | Pending | bar: Month 5 (Jun-Jul) W20
★ | MILESTONE: Champion Network Handover Completed |  | Pending | bar: Month 6 (Jul-Aug) W24
TASK 4: ADOPTION SURVEYS & SCORECARDS
4.1 | Adoption scorecard framework designed & validated | Khalil / Digibit | Not Started | bar: Month 2 (Mar-Apr) W5 to Month 2 (Mar-Apr) W8
4.2 | Baseline adoption pulse survey deployed (pre go-live) | Khalil | Not Started | bar: Month 3 (Apr-May) W9 to Month 3 (Apr-May) W12
4.3 | Baseline survey results analysed & reported | Khalil | Not Started | bar: Month 3 (Apr-May) W12 to Month 4 (May-Jun) W15
4.4 | Mid-point adoption survey deployed & results analysed | Khalil | Not Started | bar: Month 4 (May-Jun) W13 to Month 5 (Jun-Jul) W17
4.5 | Adoption scorecard Wave 1 populated & issued to Digibit | Khalil / Digibit | Not Started | bar: Month 4 (May-Jun) W16 to Month 5 (Jun-Jul) W19
4.6 | Final adoption survey deployed & change adoption score computed | Khalil | Not Started | bar: Month 5 (Jun-Jul) W19 to Month 6 (Jul-Aug) W22
4.7 | Final adoption scorecard — ≥80% target verified & signed off | Khalil / Digibit | Not Started | bar: Month 6 (Jul-Aug) W21 to Month 6 (Jul-Aug) W24
★ | MILESTONE: Adoption Scorecard Wave 1 Issued |  | Pending | bar: Month 4 (May-Jun) W16
★ | MILESTONE: Final Adoption Metrics ≥80% Confirmed & Signed Off |  | Pending | bar: Month 6 (Jul-Aug) W24
TASK 5: POST–GO-LIVE ADOPTION TRACKING
5.1 | Go-live readiness review — people & process dimensions | Khalil / Digibit | Not Started | bar: Month 4 (May-Jun) W13 to Month 4 (May-Jun) W16
5.2 | Post–go-live adoption monitoring commenced (wks 1–4) | Khalil | Not Started | bar: Month 5 (Jun-Jul) W17 to Month 6 (Jul-Aug) W21
5.3 | Weekly adoption tracker maintained | Khalil | Not Started | bar: Month 5 (Jun-Jul) W17 to Month 6 (Jul-Aug) W24
5.4 | Corrective action plan issued for low-adoption departments | Khalil | Not Started | bar: Month 5 (Jun-Jul) W19 to Month 6 (Jul-Aug) W22
5.5 | Q1 Change Management Executive Report presented | Khalil / Digibit | Not Started | bar: Month 4 (May-Jun) W15 to Month 5 (Jun-Jul) W18
5.6 | Final project review & engagement sign-off | Khalil / Digibit | Not Started | bar: Month 6 (Jul-Aug) W21 to Month 6 (Jul-Aug) W24
★ | MILESTONE: Go-Live Readiness Report Delivered |  | Pending | bar: Month 5 (Jun-Jul) W17
★ | MILESTONE: Engagement Formally Closed — Sign-Off |  | Pending | bar: Month 6 (Jul-Aug) W24
LEGEND:
Task 1: Change Management Plan
Task 2: Role-Based Training & Onboarding
Task 3: Change Champion Network
Task 4: Adoption Surveys & Scorecards
Task 5: Post–Go-Live Adoption Tracking
★ Milestone

## Deliverables Tracker
DELIVERABLES TRACKING REGISTER
# | Task | Deliverable | Description | Due Date | Owner | Status | % Complete | Review Notes | Sign-off
D1.1 | Task 1 | Change Charter | Governance structure, scope, roles & responsibilities defined and approved | Mar 2026 | Khalil | Not Started | 0
D1.2 | Task 1 | Stakeholder Impact Map | Impact and influence analysis across all MGB departments and user groups | Mar 2026 | Khalil | Not Started | 0
D1.3 | Task 1 | Approved Communication Plan | Phased communications strategy with channel, audience mapping, and execution log | Mar 2026 | Khalil / Digibit | Not Started | 0
D1.4 | Task 1 | Champion Network Roster | Directory of all activated change champions with department assignments and contact details | Apr 2026 | Khalil | Not Started | 0
D1.5 | Task 1 | Champion Session Reports (x4) | Monthly coordination session minutes, action logs, and feedback summaries | Monthly | Khalil | Not Started | 0
D2.1 | Task 2 | Training Needs Analysis | Role-by-role training gap assessment and recommended content structure | Mar 2026 | Khalil | Not Started | 0
D2.2 | Task 2 | Training Modules — All Roles | Role-based training content packs for all cohorts (operations, management, executives) | Apr 2026 | Khalil | Not Started | 0
D2.3 | Task 2 | Training Report — Cohort 1 | Attendance records, knowledge assessment results, and recommendations for operations & frontline | May 2026 | Khalil | Not Started | 0
D2.4 | Task 2 | Training Report — Cohort 2 | Attendance records, knowledge assessment results, and recommendations for management & supervisors | May 2026 | Khalil | Not Started | 0
D2.5 | Task 2 | Training Report — Cohort 3 | Attendance records, knowledge assessment results, and recommendations for executives & senior management | Jun 2026 | Khalil | Not Started | 0
D2.6 | Task 2 | Remedial Training Report | Targeted remedial training results for cohorts below adoption threshold | Jul 2026 | Khalil | Not Started | 0
D3.1 | Task 3 | Adoption Scorecard Template | Validated scorecard framework with metric definitions aligned to ≥80% adoption target | Apr 2026 | Khalil / Digibit | Not Started | 0
D3.2 | Task 3 | Baseline Adoption Survey & Results | Pre–go-live pulse survey instrument and analysed results by department | May 2026 | Khalil | Not Started | 0
D3.3 | Task 3 | Mid-Point Adoption Survey & Results | Mid-engagement survey with trend analysis and departmental comparison | Jun 2026 | Khalil | Not Started | 0
D3.4 | Task 3 | Adoption Scorecard Wave 1 | Populated scorecard with trend commentary and corrective actions for underperforming units | Jun 2026 | Khalil / Digibit | Not Started | 0
D4.1 | Task 4 | Go-Live Readiness Report | People and process readiness assessment confirming go-live preparedness | Jun 2026 | Khalil / Digibit | Not Started | 0
D4.2 | Task 4 | Weekly Adoption Tracker | Weekly metrics log covering user adoption activity and issues in first 4 weeks post–launch | Jul 2026 | Khalil | Not Started | 0
D4.3 | Task 4 | Q1 Change Management Report | Executive quarterly review report covering adoption progress, risks, and corrective measures | Jun 2026 | Khalil / Digibit | Not Started | 0
D5.1 | Task 5 | Final Adoption Survey & Results | End-of-engagement survey with change adoption score computation | Aug 2026 | Khalil | Not Started | 0
D5.2 | Task 5 | Final Adoption Scorecard (≥80%) | Verified final scorecard confirming ≥80% change adoption score — signed off by Digibit & MGB | Aug 2026 | Khalil / Digibit | Not Started | 0
D5.3 | Task 5 | Final Change Adoption Metrics Report | Consolidated adoption metrics suitable for CBN regulatory and audit review | Aug 2026 | Khalil | Not Started | 0
D5.4 | Task 5 | Handover Pack & Materials Archive | All engagement outputs, training materials, champion roster, and documentation transferred to MGB | Aug 2026 | Khalil | Not Started | 0
|  | Total Deliverables: | 22

## Risk Register
RISK REGISTER & MITIGATION PLAN
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Level | Mitigation Strategy | Owner | Status
R01 | Delayed access to MGB staff and systems for stakeholder mapping and training delivery | Access | Medium | High | High | Pre-engagement access checklist submitted to Digibit; escalation to MGB COO if delayed >5 business days | Khalil / Digibit | Open
R02 | Low staff engagement in training sessions and adoption surveys | People | Medium | High | High | Secure executive sponsorship; mandatory participation directive; champion-led promotion; gamified sessions | Digibit | Open
R03 | Resistance from department heads or mid-level management to change initiative | People | Medium | High | High | Early stakeholder impact mapping; targeted champion placement at resistance hotspots; escalation protocol | Khalil | Open
R04 | Adoption score trajectory below ≥80% at mid-point review | Performance | Low | Critical | High | Mid-point corrective action plan triggered; remedial training deployed; champion network intensified in underperforming units | Khalil / Digibit | Open
R05 | Scope creep — requests for additional training content beyond agreed modules | Scope | Medium | Medium | Medium | Strict change control process; documented scope baseline; variation order required for out-of-scope requests | Khalil / Digibit | Open
R06 | Key personnel (MGB or Digibit) unavailability affecting project continuity | Resource | Low | Medium | Low | Knowledge documentation throughout engagement; backup resource plan agreed with Digibit at kick-off | Digibit | Open
R07 | Regulatory changes (CBN guidelines) impacting training or reporting requirements | Regulatory | Low | High | Medium | Monitor CBN circulars monthly; build flexibility into training templates; quarterly compliance alignment review | Digibit | Open
R08 | Technology readiness gaps or system delays slowing adoption training delivery | Technical | Medium | Medium | Medium | Training schedule built with buffer weeks; simulation-based training as interim option if system unavailable | Khalil | Open